## Instructions
Instructions | Enter your team name as specified in the cell below. When doing cross-team acceptance testing, enter the name for the testing group. Fill-in the Test Plan worksheet with all the remaining User Stories in your Product Backlog. Since Product acceptance is from the perspective of the end-user, only add User Stories that pertain to the Owner or Buyer and do not include User Stories specifically for the REST API service (e.g. AS a developer...). As your user stories are refined, add the acceptance criteria for each user story. Use a separate worksheet to provide any specific test case data that the tester needs to use. As tests are performed in each sprint, indicate Pass/Fail. Note that there are separate columns for each sprint. The tester should add initials and a date in the comments column. If the test failed, the tester is required to add additional information about the failure. The status cell will color code based on the test results. The comments cell will color code when a test result exists but no information is entered. Save this test plan with a name formatted as "term-swen-261-sec-letter name", e.g. 2231-swen-261-10-a Speedy Racers.xslx. Submit this file per the instructions specified for the sprint submissions and cross-team testing.
Team Name | 2235-SWEN-261-03-2b-Get_The_Job_Done
Testing Team Name | fill in when doing cross-team testing

## Test Plan
User Story | Acceptance Criterion | Sprint 2 | Tester initials; date; comments (required if test failed) | Sprint 3 | Tester initials; date; comments (required if test failed)
As a helper I want to see a list of needs so that I choose what to contribute to. | Given that I am on the u-fund site when I am not on the Needs page then I must see a means to navigate to the Needs page. | Pass | OC; 3/18/24 | Pass | OC; 4/7
| Given that I am not on the Needs page when I choose the Needs page then I am taken to the Needs page. | Pass | OC; 3/18/24 | Pass | OC; 4/8
| Given that I am on the Needs page when there are no needs in the cupboard I see a message indicating that that there are no needs available to contribute. | Pass | OC; 3/18/24 | Pass | OC; 4/9
| Given that I am on the Needs page when there are needs in the cupboard then I see each need and short description. | Pass | OC; 3/18/24 | Pass | OC; 4/10
| Given that I am on the Needs page when there are needs in the cupboard then I see a means to add each need to my funding basket. | Pass | OC; 3/18/24 | Pass | OC; 4/11
As an admin, I want to have the ability to access, add, change, or delete user information to manage the system effectively. | Given I am logged in as an admin, When I navigate to the user management section, Then I can view a list of all users registered in the system. | Pass | OC; 3/18/24 | Pass | OC; 4/12
| Given I am viewing the list of users, When I select a user, Then I am presented with the user's details and options to change or delete their information. | Pass | OC; 3/18/24 | Pass | OC; 4/13
| Given I am editing a user's information, When I make changes to the user's details (e.g., update their email or role) and save these changes, Then the user's information is updated in the system, and a confirmation message is displayed. | Pass | OC; 3/18/24 | Pass | OC; 4/14
| Given I choose to delete a user, When I confirm the deletion action, Then the user's information is removed from the system, and a confirmation message is displayed. | Pass | OC; 3/18/24 | Pass | OC; 4/15
| Given I attempt any action (add, change, delete) and an error occurs (e.g., network issue, data validation error), When the action fails, Then an error message is displayed, explaining the reason for the failure and suggesting how to resolve it (if applicable). | Pass | OC; 3/18/24 | Pass | OC; 4/16
As a user I want a personal shopping cart that is unique to me and can be saved for future sessions. | Given I am a new or returning user on the e-commerce platform, When I add items to my shopping cart, Then these items are associated with my user account, ensuring my cart is unique to me. | Pass | OC; 3/18/24 | Pass | OC; 4/17
| Given I have items in my shopping cart and I log out of my account, When I log back in at a later time, Then I find all my previously added items still present in the cart, allowing me to continue my shopping session seamlessly. | Pass | OC; 3/18/24 | Pass | OC; 4/18
| Given items in my shopping cart have limited stock, When stock levels change for any item in my cart (e.g., an item becomes out of stock), Then I am promptly notified within the cart interface about the change, allowing me to make informed decisions (e.g., waitlist, remove item, select an alternative). | Pass | OC; 3/18/24 | Pass | OC; 4/19
| Given I have an active shopping session with items in my cart, When I choose to checkout, Then the checkout process uses the items from my saved shopping cart, ensuring a smooth transition from browsing to purchasing. | Pass | OC; 3/18/24 | Pass | OC; 4/20
As a User I want to be able to Checkout my cart so I can pay for the items | Given the user has added items to their shopping cart, When they navigate to the cart, Then they can see all items listed with their prices, quantities, and a total cost. | Pass | OC; 3/18/24 | Pass | OC; 4/21
| Given the user wishes to change an item's quantity or remove an item from their cart during checkout, When they adjust the item quantities or remove items, Then the cart updates to reflect these changes, including the updated total cost, before finalizing the payment.¦ | Pass | OC; 3/18/24 | Pass | OC; 4/22
| Given the user has completed the checkout process, When they return to their shopping cart, Then the cart is empty, indicating that the transaction was successfully processed. | Pass | OC; 3/18/24 | Pass | OC; 4/23
As a user I want the website to show content efficiently and react to my interactions so that I can enjoy a seamless browsing experience. | Given I am a user accessing the website, When I navigate to different pages or sections, Then the content loads quickly, without significant delays. | Pass | OC; 3/18/24 | Pass | OC; 4/24
| Given I interact with interactive elements (e.g., buttons, links), When I click or tap on them, Then the corresponding action or transition occurs promptly, providing immediate feedback to my interaction. | Pass | OC; 3/18/24 | Pass | OC; 4/25
| Given I input data into forms or fields (e.g., search bar, login form), When I type or select options, Then the website responds smoothly, without lag or latency, ensuring a seamless data entry experience. | Pass | OC; 3/18/24 | Pass | OC; 4/26
As a User I want to be able to add a Need to my cart so I can checkout. | Given I am browsing the list of Needs, When I find a Need I wish to contribute to or purchase, Then I see an “Add to Cart” button or icon next to each Need. | Fail | OC; 3/18/24; add need to cart not implemented but update cart is | Pass | OC; 4/27
| Given I click the “Add to Cart” button for a specific Need, When the action is successful, Then I receive visual confirmation (e.g., a notification, icon update) that the item has been added to my cart. | Pass | OC; 3/18/24 | Pass | OC; 4/28
| Given I have added a Need to my cart, When I navigate to my cart, Then I see the Need listed there with its details (e.g., description, quantity, contribution amount). | Pass | OC; 3/18/24 | Pass | OC; 4/29
| Given I am viewing a Need in my cart, When I decide to adjust my contribution (e.g., change quantity, donation amount), Then I can modify these details directly within the cart. | Pass | OC; 3/18/24 | Pass | OC; 4/30
| Given I have modified a Need's details in my cart, When I finalize the changes, Then the cart updates to reflect these changes, including the new total amount (if applicable). | Pass | OC; 3/18/24 | Pass | OC; 4/31
As a USER I want to CREATE AN ACCOUNT so that I CAN SAVE MY CART FOR FUTURE SESSIONS. | Given I am a new user without an account, When I select the option to create an account, Then I am directed to a registration form where I can enter my details (e.g., name, email, and password). | Pass | OC; 3/18/24 | Pass | OC; 4/32
| Given I have entered my details on the registration form, When I submit the form without filling out all required fields, Then I receive an error message indicating the fields that need to be completed. | Pass | OC; 3/18/24 | Pass | OC; 4/33
| Given I am creating an account, When I enter an email address that is already associated with an existing account, Then I receive a notification that the email is already in use and am offered the option to log in or recover my password. | Pass | OC; 3/18/24 | Pass | OC; 4/34
| Given I have filled out the registration form correctly, When I click the “Create Account” button, Then my account is created, and I am automatically logged in. | Pass | OC; 3/18/24 | Pass | OC; 4/35
| Given I am on the login page, When I enter incorrect login credentials, Then I receive an error message and the option to reset my password or try again. | Pass | OC; 3/18/24 | Pass | OC; 4/36
As a user I want to see where and when the food drop off locations are. | Given I am viewing the list of upcoming food drop-off events, When I select a specific event, Then I see detailed information about the event including the location, date, time, and any special instructions. | Fail | OC; 3/18/24; not yet implemented | Pass | OC; 4/37
As an admin I want to be able to edit the times and locations for the food drop off. | Given I am logged in as an admin on the volunteer coordination platform, When I navigate to the food drop-off management section, Then I can see a list of existing drop-off events with options to edit their times and locations. | Fail | OC; 3/18/24; not yet implemented | Pass | OC; 4/38
| Given I want to edit the details of a specific drop-off event, When I select the event from the list, Then I am presented with a form pre-populated with the current details of the event, including date, time, and location. | Fail | OC; 3/18/24; not yet implemented | Pass | OC; 4/39
| Given I am editing the details of a drop-off event, When I update the date, time, or location fields, Then I can save the changes, and the event details are updated in the system. | Fail | OC; 3/18/24; not yet implemented | Pass | OC; 4/40
| Given I want to cancel a drop-off event, When I select the option to cancel the event, Then I am prompted to confirm the cancellation, and upon confirmation, the event is removed from the system, and all associated volunteers are notified. | Fail | OC; 3/18/24; not yet implemented | Pass | OC; 4/41
As a user I want to be able to sign up to volunteer for a date, time and place. | Given I am on the volunteering platform's homepage, When I navigate to the volunteering events section, Then I see a list of upcoming volunteering events with details such as date, time, location, and the number of available volunteer slots. | Fail | OC; 3/18/24; not yet implemented | Pass | OC; 4/42
| Given I want to sign up for a volunteering event, When I click on the event I'm interested in, Then I am directed to a page displaying detailed information about the event, including the tasks involved and any prerequisites. | Fail | OC; 3/18/24; not yet implemented | Pass | OC; 4/43
| Given I have decided to volunteer for a specific event, When I find the "Sign Up" or "Volunteer" button, Then I click on it to indicate my interest in participating. | Fail | OC; 3/18/24; not yet implemented | Pass | OC; 4/44
| Given I clicked on the "Sign Up" button for a volunteering event, When I am logged in, Then I am successfully registered for the event, and the system updates the number of available volunteer slots accordingly. | Fail | OC; 3/18/24; not yet implemented | Pass | OC; 4/45
| Given I want to cancel my registration for a volunteering event, When I navigate to the event details or my profile, Then I can find an option to withdraw my registration, and upon confirmation, my slot is freed up for other potential volunteers. | Fail | OC; 3/18/24; not yet implemented | Pass | OC; 4/46